## Full Package
Full package deployment check-list - R1.4.2
Sequence | Task | Status | Time | Comments | Server | R1.4.2_Sprint5
1 | Backup 11.2.2 db and tc |  |  | Backup done of db and tc11 folder
2 | Upgrade from 11.2.2 to 11.2.3.1 |  |  | Upgrade to Patch Tc11.2.3_patch_1. NOTE: SVN Path for t4s_template dependencies: https://sbtsvn.plmcare.net/svn/0SBT-PR-TC11UPGR/trunk/DataModel/BMIDE_t4s_templates/full_update | Volume, Application
3 | Upgrade to AWC AWC3.2.1 patches |  |  | Tc11.2.1_ActiveWorkspace3.2.1_wntx64 patch installation on upgraded machine | Web + AW,Solr
4 | Install customer patch |  |  | Install customer patch Tc11.2.3.1_a01_patch_2 at server only | Volume, Render
5.1 | Install additional AWC client featues |  |  | Copy AWC CCR code from SBT-PR-TC11UPGR\branches\R1.4.2\Customization\AWC\stage\src to %AW_ROOT%\stage\src | Web + AW
Refer AWC Feature tab for further details
5.2 | Install additional AWC server featues |  |  | Manually need to copy dlls, lang, l10 and lots of things from aws2_rtserver.zip file. Check with mario | Volume
Refer AWC Feature tab for further details
6 | Upgrade to IMM IMM_11.2.3.01 |  |  | Upgrade to "IMM_11.2.3.01_win64" patch Refer document from SVN 0SBT-PR-TC11UPGR\branches\R1.4.2\Documentation\UpgradeToTC11.2.3.1\IMM_NX_Configuration.docx | Volume, Application
7 | TCVis TcVis_11231_win64 |  |  | base installation TcVis_11231_win64 Refer document from SVN 0SBT-PR-TC11UPGR\branches\R1.4.2\Documentation\TCVis_Installation.docx | Render
8 | Template deployement |  |  |  | Volume
8.1 | BT7 |  |  | 1. SBT_1PLM4BT deploy on all site CSE: SVN 0SBT-PR-TC11UPGR\branches\R1.4.2\Datamodel\SBT_1PLM4BT\output\wntx64\packaging\full_update China: SVN 0SBT-PR-TC11UPGR\branches\R1.4.2\Datamodel\Multisite\China\SBT_1PLM4BT\output\wntx64\packaging\full_update Korea: SVN 0SBT-PR-TC11UPGR\branches\R1.4.2\Datamodel\Multisite\Korea\SBT_1PLM4BT\output\wntx64\packaging\full_update USA: SVN 0SBT-PR-TC11UPGR\branches\R1.4.2\Datamodel\Multisite\USA\SBT_1PLM4BT\output\wntx64\packaging\full_update BT7_CCR_DUMMY issue while deploying template - just remove delete lines for this BT7_CCR_DUMMY object from delta_pre.xml file |  | CSE: https://sbtsvn.plmcare.net/svn/0SBT-PR-TC11UPGR/branches/R1.4.2/Datamodel/SBT_1PLM4BT/output/wntx64/packaging/full_update/2017_07_14_14-04-10 China: https://sbtsvn.plmcare.net/svn/0SBT-PR-TC11UPGR/branches/R1.4.2/Datamodel/Multisite/China/SBT_1PLM4BT/output/wntx64/packaging/full_update/2017_07_14_12-33-53 USA: https://sbtsvn.plmcare.net/svn/0sbt-pr-tc11upgr/branches/r1.4.2/datamodel/multisite/china/sbt_1plm4bt/output/wntx64/packaging/full_update/2017_07_14_13-40-16 Korea: https://sbtsvn.plmcare.net/svn/0SBT-PR-TC11UPGR/branches/R1.4.2/Datamodel/Multisite/Korea/SBT_1PLM4BT/output/wntx64/packaging/full_update/2017_07_14_14-29-26
9.1 | Configuration and code deployment |  |  | Do copy/execute scripts where necessary in below order 1. Binaries: a.1) jars: Copy jar from SVN 0SBT-PR-TC11UPGR\branches\R1.4.2\Binaries\R1.4.2_LATEST_DATE\Binaries\jar to %TC_ROOT%\portal\plugin a.2) Go to %TC_ROOT%/portal/registry and inside it execute genregxml.bat batch file b) bin: Copy dlls from SVN 0SBT-PR-TC11UPGR\branches\R1.4.2\Binaries\R1.4.2_LATEST_DATE\Binaries\bin to %TC_ROOT%/bin c) lib: Copy lib from SVN E70SBT-PR-TC11UPGR\branches\R1.4.2\Binaries\lib to %TC_ROOT%/lib d)exe: Copy following exe from 0SBT-PR-TC11UPGR\branches\R1.4.2\Binaries\R1.4.2_LATEST_DATE\Binaries\exe d.i.1) Doc_Rev_LOV_Migration.exe ->%TC_ROOT%\bin d.i.2) Processed_DocitemRev_Report.exe-> %TC_ROOT%\bin d.ii) Document Classification: d.ii.1) Please refer "Doc_Rev_LOV_Migration.docx" document at svn "0SBT-PR-TC11UPGR\branches\R1.4.2\Binaries\exe\Doc_Rev_LOV_Migration\Doc_Rev_LOV_Migration.docx" 2. Configuration: Use batch file to import Configuration Changes a) While executing any batch file for Configuration open comand promt and change directory uptill batch file location and then execute batch file No order at sub level(in case of dispatcher make to to update necessayr batch file from disapcther, module directories as per svn file) b) Using merge tool, merge dispatcher files from backup with the latest one available after patch. | Volume, Application | 1. Bin: Copy SBT_Workflow.dll from below path to %TC_ROOT%\bin https://sbtsvn.plmcare.net/svn/0SBT-PR-TC11UPGR/branches/R1.4.2/Binaries/R1.4.2_2017-07-14/Binaries/bin/SBT_Workflow.dll 2. Configuration: 2.1. 0SBT-PR-TC11UPGR\branches\R1.4.2\plmshare_test\tcconfig\test\patch\CPR_1PDM4BT_142\content\com.drwe.sbt.rac_1.1.0.0.jar 2.2 \branches\R1.4.2\Configuration\StyleSheets\Awp0BT7_CommonCompRevision.xml 2.3. https://sbtsvn.plmcare.net/svn/0SBT-PR-TC11UPGR/branches\R1.4.2\Configuration\Workflow\SR.xml ¦PR.xml¦ PR+.xml
9.2 | Dispatcher Configuration and code deployment |  |  | Do copy/execute scripts where necessary in below order 1. Binaries - a.1) dispatcher jars: Copy jar from 0SBT-PR-TC11UPGR\branches\R1.4.2\Binaries\R1.4.2_LATEST_DATE\Binaries\jar\Dispatcher\Accenture_CADIM_File_Export.jar, Accenture_Report_BOM.jar to RENDER SERVER machine at %DISP_ROOT%\DispatcherClient\lib b) exe: b.i) Copy below exes from 0SBT-PR-TC11UPGR\branches\R1.4.2\Binaries\R1.4.2_LATEST_DATE\Binaries\exe and move them to respective location of TC Dispatcher folder b.i.1) bt7_cadim_file_export.exe -> %TC_Dispatcher%\11_disp\Module\Translators\CADIM_File_Export\ b.i.2) bt7_report_bom.exe -> %TC_Dispatcher%\11_disp\Module\Translators\Report_BOM\ b.i.3) bt7_report_csv.exe -> %TC_Dispatcher%\11_disp\Module\Translators\Report_CSV\ b.i.4) bt7_report_pdbrowser.exe -> %TC_Dispatcher%\11_disp\Module\Translators\OP_Export\ | Render | a) xsl a.1) Copy 2 .xsl files from 0SBT-PR-TC11UPGR\branches\R1.4.2\Configuration\Dispatcher\Module\Translators\Report_BOM and move them to -> %TC_Dispatcher%\11_disp\Module\Translators\Report_BOM\
10 | TC Frontend Client patch |  |  | patch client using latest jars from 0SBT-PR-TC11UPGR\trunk\MRT\plmshare1123
11 | Run SQL file |  |  | 1. Execute 0SBT-PR-TC11UPGR\branches\R1.4.2\DataMigration\SQL\01_SQL.sql file at CENTAL SITE ONLY | Volume | 1. Execute 0SBT-PR-TC11UPGR\branches\R1.4.2\DataMigration\SQL\02_DOC_LOV.sql file at ALL ONLY
12 | AWC Indexing |  |  | Execute below command on SOLR machine. Run below mentioned commands: 1. %TC_ROOT%\solr-5.1.0\TcSchemaToSolrSchemaTransform.bat %TC_DATA%\ftsi 2. %TC_ROOT%\TcFTSIndexer\runTcFTSIndexer.bat -task=objdata:clear 3. %TC_ROOT%\TcFTSIndexer\runTcFTSIndexer.bat -task=objdata:index | Solr

## AWC Features
This page tells about the features to be installed for AWC. After upgrade to AWC 3.2.x some of these features can be uninstalled. Please make sure if these are still selected
Active Workspace |  | Feature: | Server:
Client
|  | Active Workspace Client (.NET) | chlupi99014srv
|  | Classification | chlupi99014srv | For more info:Refer document from SVN 0SBT-PR-TC11UPGR\branches\R1.4.2\Documentation\Classification_Command_Display_Install.docx
|  | Library Management | chlupi99014srv
|  | Relationship Browser | chlupi99014srv
|  | Workflow | chlupi99014srv
|  | Active Content | chlupi99014srv
|  | Requirements Management | chlupi99014srv | For more info: Refer document from SVN 0SBT-PR-TC11UPGR\branches\R1.4.2\Documentation\Export_to_Excel_Command_Display_Install.docx
Server Extensions
|  | Active Workspace | chlupi99012srv
|  | Active Content Structure | chlupi99012srv
|  | Relationship Viewer | chlupi99012srv
|  | Workflow | chlupi99012srv
|  | Requirements Management | chlupi99012srv
|  | Library Management | chlupi99012srv
Indexing Server
|  | Active Workspace Indexing Engine | chlupi99010srv
|  | Active Workspace Indexer | chlupi99010srv